## Individual
Team Use only | Group work asset-author details
Individual accounting of work done for the project
All software development done by the team should be recorded in this file
Some columns may not be applicable if coding is not involved.
Function name is usually class::method
The work breakdown sheet (group declaration sheet) is a summary of the information in this file. See last page of unit guide
Only one copy of this file should be submitted.
Team members Name | File Name | Function/model name | Lines of code | Comment lines | Purpose of function/model | Used/called by filename:functionName/model name | Estimated time for task | Actual time taken for task
Vladislav Kennebury | Portal.h | All functons | 0 - 81 | Doxygen | Declarations for all functions within | Portal.cpp | 15 min | 15 min
| Portal.cpp | All functons | 0 - 57 | Standard (//) | Implementation of portal | DisplayShaysWorld, DisplayWrathWorld | 1h | 1h
| DisplayShaysWorld.h | Texture declarations | 280 - 304 | Doxygen | Declarations for all textures within the class | DisplayShaysWorld.cpp | 20min | 20min
| DisplayShaysWorld.cpp | Portal Implementation | 48 - 92 | Standard (//) | Set locations for portals within Shay's world | main.cpp | 2h | 2h
| DisplayShaysWorld.cpp | Bounding boxes | 246 - 319 | Standard (//) | Set bounding boxes for bins and posts | main.cpp | 1h | 1h
| DisplayShaysWorld.cpp | Texture dimensions | 1093 - 1168 | Standard (//) | Set dimenions and declare all textures | DisplayShaysWorld.cpp | 1h | 1h
| DisplayShaysWorld.cpp | 2nd Floor Balcony extensions | 1738 - 1741 | Standard (//) | Model and display two sides of 2nd floor balcony | DisplayShaysWorld.cpp | 30min | 30min
| DisplayShaysWorld.cpp | drawStairs() | 3373 - 3629 | Standard (//) | drawing the display and teture of the stairs | DisplayShaysWorld.cpp | 3h | 5h
| DisplayShaysWorld.cpp | createPlains() | 373 - 411 | Standard (//) | Plains for stairs | DisplayShaysWorld.cpp | 2h | 4h
| DisplayShaysWorld.cpp | displayExtras() | 4083 - 4223 | Standard (//) | Texture assigning for extras (bins, posters) | DisplayShaysWorld.cpp | 1h | 1h
| DisplayShaysWorld.cpp | drawExtras() | 4358 - 4885 | Standard (//) | Re-orient textures and map to display | DisplayShaysWorld.cpp | 2-3h | 5h
Charlie Sewell | AABB.h | all functions in file | 0-end | Doxygen Comments | to make doxygen work | Doxygen | 20 min | 20 min
| AABBLinkedList.h | all functions in file | 0-end | Doxygen Comments | to make doxygen work | Doxygen | 10 min | 15 min
| AABBNode.h | all functions in file | 0-end | Doxygen Comments | to make doxygen work | Doxygen | 15 min | 15 min
| camera.h | all functions in file | 0-end | Doxygen Comments | to make doxygen work | Doxygen | 20 min | 30 min
| cameraMap.h | all functions in file | 0-end | Doxygen Comments | to make doxygen work | Doxygen | 10 min | 20 min
| collision.h | all functions in file | 0-end | Doxygen Comments | to make doxygen work | Doxygen | 15 min | 20 min
| PlainLinkedList.h | all functions in file | 0-end | Doxygen Comments | to make doxygen work | Doxygen | 20 min | 10 min
| PlainNode.h | all functions in file | 0-end | Doxygen Comments | to make doxygen work | Doxygen | 20 min | 20 min
| texturedPolygons.h | all functions in file | 0-end | Doxygen Comments | to make doxygen work | Doxygen | 20 min | 15 min
| texturedPolygons.cpp | TexturedPolygons::LoadTexture(*const char filename) | 26-35 | standard | allows loading of png images into an array | ShaysWorld::CreateTextures() | 15 min | 45 min
| texturedPolygons.cpp | TexturedPolygons::CreatePNGTexture() | 93-99 | standard | allows png images to be used as textures | ShaysWorld::CreateTextures() | 15 min | 10 min
| .gitignore |  | 0-end |  | ignores certain files on github | used by github to minimise merge conflicts | 30 min | 1 hour
| Creating of splash screens |  |  |  | Created new start and finish splash screens |  | 30 min | 30 min
Connor Nicholson | main.cpp | All user input functions | 184-359 |  | Implement key buffering | glutKeyboardFuc | 1hr | 1hrs
| camera.cpp | RotateCamera | 304-319 |  | Allow camera to look in all directions with mouse | MouseMove | 1hr | 2hrs
| main.cpp | Display() | 88-162 |  | Moved all the display functions out of main.cpp and rewrote display() to reflect the new class design |  | 1hr | 1.5hr
| DisplayShaysWorld.cpp | relevant display/draw funcions (bricks/pavement/pillars/AABBs ect) | Various spots all over file |  | Modelled the main structure of the courtyard | main.cpp display() | 3hr | 5hr
| DisplayWrathWorld.h &DisplayWrathWorld.cpp | All functions | All lines |  | Display Wrath World | main.cpp display() | 2hr | 5hr